## Sys Planning
Region | Project Title | Project Status | Project Sponsor | Justification
ABUJA | Construction of Gwagwalada- New Apo 330kV DC Line | New | Nil | Required for evacuation of the 300MW First Phase of 900MW NNPC Gas power plant at Gwagwalada.
ABUJA | Upgrade of Shiroro-Triple Point(Mararaba)-Jebba 330kV DC line. | New | Nil | Required for more capacity of South - North power transfer and vice versa generators.
ABUJA | Installation of Mobile and variable Capacitor Bank in Bida, Suleija | New | Nil | required to address low voltage in the area and to supply the forecasted demand.
BENIN | Completion of Ihovbor-Akure-Osogbo 330kV DC Line | Ongoing | FGN/IGR | Required for evacuation of more power from Ihovbor as well as system security and reliability
BENIN | Completion of Turn in Turn out of existing Ihovbor-Osogbo 330kV Line at Akure 330/132/33kV substation | Ongoing | FGN/IGR | Required to divert the load at Akure and Ado Ekiti from Osogbo to Akure 330kV substation.
BENIN | Turn in Turn out of Benin-Ajaokuta 330kV line at Ihovbor | New | Nil | Required for evacuation of both Azura and Ihovbor generation and for reliability of supply.
BENIN | Upgrade of Benin-Omotosho 330kV Line to Quad Circuit 330kV line | New | Nil | Required for Evacuation of generation from Benin towards Lagos area.
LAGOS | Completion of Omotosho-Epe-Ajah 330kV DC Line and 330/132/33kV Substation at Epe | Ongoing | FGN/IGR | The project is the evacuation corridor for the 900MW Pacific power plant which has almost completed. It also provides reliability for the Benin-Egbin and Omotosho – Ikeja West 330kV lines.
LAGOS | Construction of Ikeja West-Arigbajo 330kV DC Line | Committed | JICA | Required for reliability of Olorunshogo-Ikeja West 330kV line. JICA
LAGOS | Construction of Arigbajo-Oshogbo 330kV DC Line | Committed | JICA | Required for reliability of Ayede- Oshogbo 330kV line.
LAGOS | Construction of Omotosho-Ogijo 330kV DC Line and Ogijo 330/132/33kV Substation | Committed | JICA | Required to provide reliability for Benin-Egbin and Benin-Omotosho330kV lines.
ENUGU | Construction of Delta-Okpai 330kV DC line | New |  | Support evacuation of Okpai Phase II
BAUCHI | Commissioning of Second Kaduna-Jos 330kV Line | Almost Completed | AfDB | Required for system security in year 3.
BAUCHI | Construction of Second Jos-Gombe 330kV Line | New | NIL | Critical for system reliability and security in the North Eastern part of the country and is required in year 1.
BAUCHI | Completion of Transposition on the Uguaji-Jos 330kV line
BAUCHI | Construction of Second Jos-Gombe 330kV Line | New | NIL | Critical for system reliability and security of supply in the North Eastern part of the country.
BAUCHI | Construction of 330kV line from Makurdi to Jalingo | New | NIL | For System Reliability to create a ring network for the North East region
BAUCHI | Construction of 330kV line from Yola to Maiduguri | New | NIL
KADUNA | Kainji-Kalgo 330kV DC line and Kalgo 330/132/33kV Substation | Ongoing | AFD | AFD North core projects is required and recommended in year 5. This project will also provide network security for the north west.
KADUNA | Turn in Turn out of existing Kainji - Birnin Kebbi 330kV Line at Kalgo | Ongoing | AFD | Recommended to improve system reliability and is required in year 1. This Project is captured in the North Core Transmission Projects.
KADUNA | Reinforcement of Shiroro-Kaduna 330kV double circuit transmission line to Quad conductor | New | Nil | Required for System security and reliability and for more evacuation from Zungeru Hydro power station towards Kaduna.
KADUNA | Mararaba- Millenium City 330kV LIne | New | Nil | Required for system security and additional route for power transfer to and from North west.
KANO | Completion of Second Kaduna-Kano 330kV Line including Turn in Turn out into proposed Zaria 330/132kV SS | Ongoing | FGN/IGR | Required both for system security in the North West and to meet demand of Kano Disco.
Port Harcourt | Additional 2X162MVA Intrbus Transformers at Afam IV 330/132/33kV Substation | New | NIL | Required for more evacuation from Rivers IPP, Afam Fast power.
Port Harcourt | 1X162MVA Interbus transformer at Afam I -III Substation | New | NIL | Required for more evacuation from Rivers IPP, Afam Fast power.
Port Harcourt | Turn in Turn out of Afam to Onne 330kV line into Rivers IPP | New | NIL | Required to evacuate second generationn Unit of Rivers IPP.

## All
S/N | Disco Rank | Disco | TCN Project Description | Station 1 | Station 2 | Finance Source | Type
1 | 1 | Abuja | Reconductoring of Katampe-Kubwa 132kV line | Katampe | Kubwa | Tariff | Line Reconductoring
2 | 2 | Abuja | Reconductoring of Apo-Karu-Keffi-Akwanga line | Apo | Akwanga | Tariff | Line Reconductoring
3 | 3 | Abuja | Reconductoring of Akwanga – Lafia Line | Akwanga | Lafia | Tariff | Line Reconductoring
4 | 4 | Abuja | Reconductoring of Lokoja - Obajana 330KV Line | Lokoja | Obajana | Tariff | Line Reconductoring
5 | 5 | Abuja | Reconductoring of Shiroro-Minna 132kV DC line | Shiroro | Minna | Tariff | Line Reconductoring
6 | 6 | Abuja | 30MVAr Capacitor Bank |  |  | Tariff | Power Qaulity
7 | 6 | Abuja | 50MX Reactor |  |  | Tariff | Power Qaulity
8 | 1 | Benin | a. Replacement of the faulty 1x150MVA, 330/132kV Power Transformer b. Upgrading of 2x60MVA with 2x100MVA, 132kV/33kV, Power Transformers c. Construction of additional 2X33kV Feeder Bays | Asaba 132/33kv |  | SLA | Substation Reinforcement
9 | 2 | Benin | " Reinforcement with 1 x150MVA 330/132kV Power Transformers" Reinforcement with 1 x 100MVA 132/33KV Power Transformer Replacement of High Voltage Switchgears, and Associated Equipment. Replacement of Obsolete Control and Relay Panels with Digital Control System | Benin 330/132/33KV |  | WB/NETAP | Substation Reinforcement
10 | 3 | Benin | Upgrading of 2 x 30MVA with 2x 60MVA,132/33kV Power Transformers. o Replacement of High Voltage Switchgears, Control & Relay panel with Digital Control system and o Conversion of 6nos. 33kV Indoor to 8No Outdoor. Rehabilitation of control room | Ondo 132/33kv |  | WB/NETAP | Substation Reinforcement
11 | 4 | Benin | o Replacement of defective 1x 60MVA 132/33kV with a new 1x 1000MVA 132/33KV Power Transformer o Replacement High Voltage Switchgears, and Associated Equipment o Installation of 4 No Additional Feeder Bays at Effurun | Effurun 132/33kv |  | WB/NETAP | Substation Reinforcement
12 | 5 | Benin | Reconductoring of undersized conductor on the 132KV line between Ughelli and Effurun (10Km) | Ughelli | Effurun | SLA | Line Reconductoring
13 | 6 | Benin | Reconductoring of 132kV Oshogbo - Akure Single Circuit transmission line | Oshogbo | Akure | SLA | Line Reconductoring
14 | 7(a) | Benin | Construction of 2 numbers of additional 33kV Line Bays | Ihovbor 132/33KV |  | SLA | Substation Reinforcement
15 | 7(b) | Benin | Upgrade of 60MVA (T1) to 1 x 100MVA | Ihovbor 132/33KV |  | PPI Phase 1 | Substation Reinforcement
16 | 8 | Benin | 2 X 150MVA 330/132kV S/S and 2 X 60MVA 132/33kV substation, Akure | Akure 330/132/33KV |  | FGN/IGR | Ongoing Substation
17 | 9 | Benin | Construction and Installation of 2x60MVA, 132/33KV Substation at Ijesha-Isu with 6x132KV Line bays Extension/Switching station at Ado-Ekiti (Ikere) | Ijesha-Isu 132/33KV |  | FGN/IGR | Ongoing Substation
18 | 10 | Benin | Construction and Installation of 2x60MVA, 132/33KV Substation at Ilupeju and 2x132KV Line bays Extension at Ijesha-Isu | Ilupeju 132/33KV |  | FGN/IGR | Ongoing Substation
19 | 11 | Benin | Construction of 1 x 60MVA, 132/33kV Substation at Kwale | Kwale 132/33KV |  | FGN/IGR | Ongoing Substation
20 | 12 | Benin | Construction of Ado-Ekiti (Ikere)-Ijesha Isu 132kV Double Circuit Transmission Line | Ado Ekiti 132/33KV | Ijesa Isu 132/33KV | FGN/IGR | Ongoing Substation
21 | 13 | Benin | 2x 150MVA 330/132KV substation at Omotosho | Omotosho 132/33KV |  | FGN/IGR | Ongoing Substation
22 | 14 | Benin | 2x60MVA 132/33kV substation at Okeagbe, Ondo State and line bays extension at Obajana | Okeagbe 132/33KV |  | FGN/IGR | Ongoing Substation
23 | 15 | Benin | 2x60MVA, 132/33kV Substation at Ose LGA Headquarters, Ondo State | Ose 132/33KV |  | FGN/IGR | Ongoing Substation
24 | 16 | Benin | Construction of Ijesha-Isu - llupeju 132kV Double Circuit Transmission Line | Ijesha-Isu 132/33KV | Ilupeju 132/33KV | FGN/IGR | New Line
25 | 17 | Benin | Construction of 2x60MVA, 132/33KV Substation at Ikare-Akoko and 2x132KV Line bays Extension at Okeagbe | Ikare-Akoko 132/33KV |  | FGN/IGR | Ongoing Substation
26 | 18 | Benin | Construction of 132kV Okeagbe-Ikare-Akoko Double Circuit Transmission Line (15km) | Okeagbe 132/33KV | Ikare-Akoko 132/33KV | FGN/IGR | New Line
27 | 19 | Benin | a. Replacement of 3No 132kV and 9Nos 33kV Current transformers and b. Differential relay at Oghara 132kV TS to restore the standby 30MVA power transformer | Oghara 132/33KV |  | SLA | Substation Reinforcement
28 | 20 | Benin | Upgrading of faulty 1x30MVA, 132/33kV Transformer with 1x60MVA power transformer | Afisere 132/33kV |  | SLA | Substation Reinforcement
29 | 21 | Benin | a. Replacement of faulty grounding on 1x40MVA, 132/33kV. b. Replacement of differential relay and surge Arrester on 1x40MVA transformer. | Okada 132/33KV |  | SLA | Substation Reinforcement
30 | 22 | Benin | Reconstruction of one of Delta-Benin 330kV Transmission Line (107 km) Double Circuit to Quad Conductor 330 Double Circuit Line | Delta 330/132/33KV | Benin 330/132/33KV | AFDB/NTEP | Line Reconstruction
31 | 23 | Benin | Construction of new Double Circuit (DC) 132kV Okada-Gilli-Gilli | Okada 132/33KV | Gilli-Gilli 132/33KV | AFDB/NTEP | New Line
32 | 24 | Benin | Construction of new DC Transmission Line 132kV Sapele - Odilli DC Transmission Line | Sapele 132/33KV | Odilli 132/33KV | AFDB/NTEP | New Line
33 | 25 | Benin | Upgrade of 30MVA (T1) to 1 x 60MVA | Amukpe 132/33KV |  | PPI Phase 1 | Substation Reinforcement
34 | 26 | Benin | Reconductoring of Irrua- Okpilai 132kV line (43km) with Turn In- Turn Out Tower at Okpila 132kV Substation. | Irrua 132/33KV | Okpilla 132/33KV | Reconductoring | Line Reconductoring
35 | 27 | Benin | a) 2X60 MVA,132/33kV transformers 6 X 33kV feeder bay | Gilli-Gilli 132/33KV |  | AFDB/NTEP | New Substation
36 | 28 | Benin | Construction of 1 x 150MVA, 330/132kV Substation at Okpai | Okpai 132 |  | FGN/IGR | Ongoing Substation
37 | 30 | Benin | Construction of 132kV Okpai-Kwale DC Transmission Line | Okpai 132/33KV | Kwale 132/33KV | FGN/IGR | New Line
38 | 31 | Benin | Reconductoring of Irrua - Benin 132kV line (81km) with Turn In- Turn Out Tower at Irrua 132kV Substation. | Irrua 132/33KV | Benin 132/33KV | Reconductoring | Line Reconductoring
39 | 32 | Benin | Reinforcement with 1 x 100MVA 132/33KV Power Transformer | Delta 330/132/33KV |  | WB/NETAP | Substation Reinforcement
40 | 33 | Benin | Supply and installation of 100MVA 132/33KV power Transformer and associated Switchgears at | Irrua 132/33KV |  | WB/NETAP | Substation Reinforcement
41 | 34 | Benin | Reinforcement with 1 x 150MVA 330/132kV Interbus Transformer, | Delta 330/132/33KV |  | WB/NETAP | Substation Reinforcement
42 | 35 | Benin | Replacement of High Voltage Switchgears, and Associated Equipment. Replacement of Obsolete Control and Relay Panels with Digital Control System | Effurun 132/33KV |  | WB/NETAP | Substation Reinforcement
43 | 36 | Benin | Construction of complete new 132/33kV Substation at Gilli-Gilli | Gilli-Gilli 132/33KV |  | AFDB/NTEP | New Substation
44 | 37 | Benin | Transformers Spares: Power Transformers (2x150MVA) | TCN |  | SLA | SLA Equipment
45 | 38 | Benin | Transformers Spares: Power Transformers (2x100MVA) | TCN |  | SLA | SLA Equipment
46 | 39 | Benin | Transformers Spares: Power Transformers (2x60MVA) | TCN |  | SLA | SLA Equipment
47 | 40 | Benin | 1 x 60 MVA Mobile Substations | TCN |  | SLA | SLA Equipment
48 | 1 | Eko | Omotosho-Epe DC Line | Omotosho | Epe | Tariff | Ongoing Line
49 | 2 | Eko | Construction of 2X150MVA, 330/132kV and 2X60 MVA, 132/33kV substations at Epe | Epe |  | Tariff | New Substation
50 | 3 | Eko | Construction of 2X150MVA, 330/132kV and 2X60 MVA, 132/33kV substations fully equipped | Lekki FTZ |  | Tariff | New Substation
51 | 4 | Eko | Epe - Lekki EPZ(25km) 330kv Double Circuit Transmission Line | Epe | Lekki FTZ | Tariff | New Line
52 | 5 | Eko | 132 kV DC line from Epe TS to Eleko Junction TS | Epe | Eleko Junction TS | Tariff | Proposed Line
53 | 6 | Eko | Construction of 2 X 60MVA 132/33kV Substation at Eleko TS | Election Junction |  | Tariff | Proposed Substation
54 | 7 | Eko | 132 kV DC line from Epe TS to Oko--Abe TS | Epe | Oko Abe | Tariff | New Line
55 | 8 | Eko | Construction of 2 X 60MVA 132/33kV Substation at Oko-Abe | Oko Abe |  | Tariff | New Substation
56 | 9 | Eko | Construction of 12.5km of new 330kV double circuit line from new Ejio 330/132/33kV substation to Olorunsogo 330kV switchyard inclusive of 1.5km 2x 330KV DC multi circuits line | Ejio | Olorunshogo | JICA | New Line
57 | 10 | Eko | Construction of 29.6km of new 330kV double circuit line from new Ejio 330/132/33kV substation to Ajegunle (New Agbara) 330/132/33kV substation | Ejio | New Agabra | JICA | New Line
58 | 11 | Eko | Construction of 36.2km of new 132kV double circuit line from New Agbara (Ajegunle) 330/132/33kV substation to the proposed Badagary 132/33kV substation. | New Agbara | Badagry | JICA | New Line
59 | 12 | Eko | Construction of complete new 330/132/33kV AIS substation at Ajegunle (New Agbara) | New Agbara |  | JICA | New Substation
60 | 13 | Eko | Construction of 2 X 60MVA 132/33kV substation at Badagary | Badagary |  | JICA | New Substation
61 | 1 | Enugu | Construction of 2x60 MVA 132kV substation Nnewi | Nnewi |  | Tariff | Ongoing Substation
62 | 2 | Enugu | Completion of Nnewi 2x60MVA Transmission project and 132kV Onitsha-Nnewi line. (to reduce Feeder length of 189.96km) | Nnewi | Onitsha | Tariff | Ongoing Line
63 | 3 | Enugu | Complete Installation of 100MVA, 132/33KV.GCM Onitsha | Onitsha |  | Tariff | Ongoing Substation
64 | 4 | Enugu | 2X60MVA,132/33kV transformers,NINTH MILES | Ninth Mile |  | Tariff | Ongoing Substation
65 | 5 | Enugu | Complete installation of 1 x 60MVA, 132/33kV Transformer OJI o (to stop Load sheddding on Udi, Achi, Oji-Urban and Orumba 33kV Feeders) | Oji |  | Tariff | Ongoing Substation
66 | 6 | Enugu | Construction/Completion of Arochukwu 1 X 40MVA. | Arochukwu |  | Tariff | Ongoing Substation
67 | 7 | Enugu | Construction /Completion of Orlu 2 X 60MVA. (to reduce Orlu Feeder length of 265.22km and improve supply to Orlu and Akokwa) | Orlu |  | Tariff | Ongoing Substation
68 | 8 | Enugu | Upgrading of 330kV Onitsha - Enugu Transmission Line | Enugu |  | Tariff | Ongoing Substation
69 | 9 | Enugu | Construction/Completion of Okigwe 2 X 60MVA T/S. (to reduce Okigwe Feeder length of 399.37km and improve supply to Okigwe, Mbaise and Orlu) | Okigwa |  | Tariff | Ongoing Substation
70 | 10 | Enugu | o Construction of 2x60MVA, 132/33kV substation at Amasiri, Afikpo | Amasiri |  | Tariff | Ongoing Substation
71 | 11 | Enugu | Completion of Installation of 1 X 60MVA Power TRF in Nibo . (to reduce Agulu Feeder length of 220.29km and Neni Feeder length of 113.44km) | Nibo |  | Tariff | Ongoing Substation
72 | 12 | Enugu | Completion of the 2 X60MVA Project.Abor Mbaise | Abor Mbaise |  | Tariff | Ongoing Substation
73 | 13 | Enugu | Installation of 2 X 60MVA at Egbu and replacement of bad 33KV Breakers. (to reduce Airport Feeder length of 180.26km and improve supply to Ngo-Okpala) | Egbu |  | Tariff | Ongoing Substation
74 | 14 | Enugu | o Construction of 2x60MVA, 132/33kV substation at Ideato | Ideato |  | Tariff | Ongoing Substation
75 | 15 | Enugu | Construction of 2x30/40MVA 132/33kV substation MBALANO | Mbalano |  | Tariff | Ongoing Substation
76 | 16 | Enugu | Construction of 2x60MVA, 132/33kV substation NENWE | Nnewe |  | Tariff | Ongoing Substation
77 | 17 | Enugu | o Construction of 2x60MVA, 132/33kV substation UMUCHU,IBUGHUBU | Umuchu, Ibughubu |  | Tariff | Ongoing Substation
78 | 18 | Enugu | Construction of 2x60MVA, 132/33kV Substation ,AGULERI | Aguleri |  | Tariff | Ongoing Substation
79 | 19 | Enugu | Construction of 2x60MVA, 132/33kV substation at Ifitedunu and 2x132kV line bays extension at Onitsha. | Onitsha |  | Tariff | Ongoing Substation
80 | 1 | Ibadan | Uprating and Dualization of the Ayede-Sagamu-Ijebu ode 132KV line . | Ayede | Ijebu Ode | Tariff | Line Reconstruction
81 | 2 | Ibadan | Installation of additional 100MVA, 132/33kV transformer at Ibadan North 330kV/132kV/33kV TS | Ibadan North |  | Tariff | Substation Reinforcement
82 | 3 | Ibadan | Reconductoring of Eleyele to Ibadan North 132Kv line | Eleyele | Ibadan North | Tariff | Line Reconductoring
83 | 4 | Ibadan | Upgrading of 1x40MVA & 1x45MVA Mobitra to 1x100MVA, 132/33kV & 40MVA,132/33KVTransformer including 2x33kV feeder bays at Jericho 132 | Jericho |  | Tariff | Substation Reinforcement
84 | 5 | Ibadan | Replacement of faulty 60MVA,132/33kV, Transformer at Ijebu-ode TS | Ijebu Ode |  | Tariff | Substation Reinforcement
85 | 6 | Ibadan | Completion of 100MVA,132/33kV upgrade at Ota TS | Ota |  | Tariff | Substation Reinforcement
86 | 7 | Ibadan | Upgrading of Iwo 1 x 40MVA, 132/33kV to 60MVA, 132/33kV Transformer | Iwo |  | Tariff | Substation Reinforcement
87 | 8 | Ibadan | Construction of 1x60MVA,132/33kV Ayede 132 to Eleyele 132kV | Eleyele |  | FGNPC | Ongoing Substation
88 | 9 | Ibadan | Construction of 2x60MVA 132/33KV Substation at Interchange 132kV | Sagamu Interchange |  | Tariff | Proposed Substation
89 | 10 | Ibadan | Installation of additional 60MVA, 132/33kV transformer at Ganmo 330/132/33kV Ts | Ganmo |  | Tariff | Substation Reinforcement
90 | 11 | Ibadan | Construction of 2 x 60MVA 132/33kV Substation at Ogbomosho 132kV | Ogbomosho |  | Tariff | Ongoing Substation
91 | 12 | Ibadan | Installation of 1x 60MVA at Ile-Ife 132kV/33kV TS | Ile-Ife |  | Tariff | Substation Reinforcement
92 | 13 | Ibadan | Construction of complete new 1x150MVA, 330/132kV with 2x60MVA, 132/33kV at Asejire | Asejire |  | Tariff | Ongoing Substation
93 | 14 | Ibadan | Construction of 1x60MVA 132/33KV Substation at Sapaade 132kV | Sapaade |  | Tariff | Ongoing Substation
94 | 15 | Ibadan | Construction of complete new 330/132/33kV AIS substation at Likosi (Ogijo) at Likosi 330/132/33 | Likosi |  | JICA | New Substation
95 | 16 | Ibadan | Construction of complete new 330/132/33kV AIS substation at Ejio (Arigbajo) at Ejio 330/132/33 | Ejio |  | JICA | New Substation
96 | 17 | Ibadan | Construction of complete new 330/132/33kV AIS substation at Ajegunle (New Agbara) 330/132/33 | New Agbara |  | JICA | New Substation
97 | 1 | Ikeja | Upgrade of Ikeja West-Alimosho-Ogba(-Alausa)-Otta-Papalanto Ring | Ikeja West | Otta | Tariff | Line Reconductoring
98 | 2 | Ikeja | Reinforcement with addition of 1 x 100MVA 132/33kV Power Transformer at Alausa TS | Alausa |  | Tariff | Substation Reinforcement
99 | 3 | Ikeja | Upgrading of T1 30MVA To 60MVA transformer at Itire TS | Itire |  | Tariff | Substation Reinforcement
100 | 4 | Ikeja | Completion of conversion of 33kV indoor breaker to outdoor breaker at Akoka TS | Akoka |  | Tariff | Substation Reinforcement
101 | 5 | Ikeja | Upgrade 30MVA to 100MVA at Maryland TS | Maryland |  | Tariff | Substation Reinforcement
102 | 6 | Ikeja | Upgrading of 2 x 30MVA transformer to 2 X 60MVA transformer at Amuwo TS | Amuwo |  | Tariff | Substation Reinforcement
103 | 7 | Ikeja | Reinforcement with addition of 1 x 60MVA 132/33kV Power Transformer at Oke Aro TS TS | Oke Aro |  | Tariff | Substation Reinforcement
104 | 8 | Ikeja | Upgrading of 45MVA transformer 60MVA at Isolo TS | Isolo |  | Tariff | Substation Reinforcement
105 | 9 | Ikeja | Construction of Additional Bays at Ejigbo TS | Ejigbo |  | Tariff | Substation Reinforcement
106 | 10 | Ikeja | Construction of Additional Bays at Ogba TS | Ogba |  | Tariff | Substation Reinforcement
107 | 11 | Ikeja | Upgrade of Egbin-Ikorodu line | Egbin | Ikorodu | Tariff | Line Reconductoring
108 | 12 | Ikeja | Reinforcement with addition of 1 x 60MVA 132/33kV Power Transformer at Oworo TS | Oworo |  | Tariff | Substation Reinforcement
109 | 13 | Ikeja | Upgrade of Akangba-Isolo line | Akangba | Isolo | Tariff | Line Reconductoring
110 | 14 | Ikeja | 132kV Multi-Circuit Oke Aro to Alausa Transmission Line | Oke Aro | Alausa | NPDHC | Ongoing Line
111 | 15 | Ikeja | Propose KARA/BERGER 132/33kV Station. | Kara/berger |  | Tariff | Proposed Substation
112 | 1 | Jos | Completion of Transposition on the Uguaji-Jos 330kV line | Ugwuaji | Jos | Tariff | Existing
113 | 2 | Jos | Construction of the Makeri-Pankshin 132KV DC Line. | Makeri | Pankshin | Tariff | Ongoing Line
114 | 3 | Jos | Construction of complete new 132/33kV substation at Biliri | Biliri |  | WB/NETAP | Ongoing Substation
115 | 4 | Jos | Construction of complete new 330/132/33kV Substation at Bauchi by turning in and turning out of the existing 330kV Single Circuit Jos-Gombe line at Bauchi | Bauchi |  | AFD NOR CORR | New Substation
116 | 5 | Jos | Construction of the Alkaleri 132/33kV substation | Alkaleri |  | Tariff | Proposed Substation
117 | 6 | Jos | Construction of the Misau 132/33kV substation | Misau |  | Tariff | Proposed Substation
118 | 1 | Kaduna | Construction of complete new 330/132/33kV Substation at Millennium City, Kaduna by turning in and turning out of the existing 330kV DC Kaduna Jos line at Millennium City, | Millennium City |  | AFDB/NTEP | New Substation
119 | 2 | Kaduna | Construction of complete new 330/132/33kV Substation at New Sokoto | Sokoto |  | AFD NOR CORR | New Substation
120 | 3 | Kaduna | Installation of 1x60 MVA, 132/33kV power transformer at Sokoto 132/33kV TS | Sokoto |  | SLA | Substation Reinforcement
121 | 4 | Kaduna | Construction of complete new 132/33kV Substation at Rigasa by turning in and turning out of the existing 132kV DC Kaduna Zaria line at Rigasa | Rigasa |  | AFDB/NTEP | New Substation
122 | 5 | Kaduna | Construction of complete new 330/132/33kV Substation at Zaria by turning in and turning out of the existing 330kV SC Kaduna Kano line at Zaria, | Zaria |  | AFDB/NTEP | New Substation
123 | 6 | Kaduna | Upgrading Of Existing 90MVA at Birnin Kebbi TS | Birnin Kebbi |  | WB/NETAP | Substation Reinforcement
124 | 7 | Kaduna | Construction of complete new 132/33kV Substation at Jaji by turning in and turning out of the existing 132kV DC Kaduna - Zaria line at Jaji | Jaji |  | AFDB/NTEP | New Substation
125 | 8 | Kaduna | Upgrading of 1x30 MVA to 1x60 MVA, 132/33kV Transformer at Gusau 132/33kV TS | Gusau |  | SLA | Substation Reinforcement
126 | 9 | Kaduna | Construction and installation of 1x45MVA Mobitra 132/33kV down dropper (on existing B/Kebbi-Sokoto 132kV S/C transmission line) TS at Argungu | Argungu |  | SLA | New Substation
127 | 10 | Kaduna | Installation of 1X150MVA 330/132/33kV transformer at Mando TS | Mando |  | Tariff | Substation Reinforcement
128 | 11 | Kaduna | Additional 132/33kv Transmission Station At Eastern Byepass Kaduna To Take Care Of The Growing Expansion In The Region | Eastern ByePass (Kaduna) |  | Tariff | Proposed Substation
129 | 12 | Kaduna | Construction of new substation at New Industrial Zone along Kaduna – Abuja express way | New Industrial Zone (Kaduna Abuja Express Way) |  | Tariff | Proposed Substation
130 | 13 | Kaduna | Construction and Installation of 2x60MVA, 132/33KV Substation at Kafanchan with 2x132KV Linebays at Jos | Kafanchan |  | Tariff | Ongoing Substation
131 | 14 | Kaduna | Construction of complete new 330/132/33kV Substation at Kalgo | Kalgo |  | AFD NOR CORR | New Substation
132 | 1 | Kano | Mando - Kumbotso 2nd 330kV Line | Mando | Kumbotso | AFDB/NTEP | New Line
133 | 2 | Kano | Walalambe 132KV | Walalambe |  | Tariff | New Substation
134 | 3 | Kano | Jogana 330kV | Jogana |  | AFD NOR CORR | New Substation
135 | 4 | Kano | Reconductoring of Kumbotso - Dakata 132kV line | Kumbotoso | Dakata | Tariff | Line Reconductoring
136 | 5 | Kano | Reconstruction of Kano - Dan Agundi 132kV single circuit transmission line | Kumbotoso | Dan Agudi | Tariff | Line Reconductoring
137 | 6 | Kano | Refurbishment of all 132kV sub-stations existing capacitor Banks and installation of additional ones in stations where there is non within KEDCO operational area for power quality |  |  | Tariff | Power Qaulity
138 | 7 | Kano | Rimin Zakara 330KV | Rimin Zakara |  | WB/NETAP | Ongoing Substation
139 | 8 | Kano | Reconductoring of Kumbotso - Hadeija | Kumbotoso | Hadeija | Tariff | Line Reconductoring
140 | 9 | Kano | Dan- Gwauro 2x60MVA, 132/33kV | Dan-Gwauro |  | Tariff | Proposed Substation
141 | 10 | Kano | Dawanau 2x60MVA, 132/33kV | Dawanau |  | Tariff | Proposed Substation
142 | 11 | Kano | Bela/Tagurza 2x60MVA, 132/33kV TS | Bela/Tagurza |  | Tariff | Proposed Substation
143 | 12 | Kano | Katsina 330KV | Katsina |  | Tariff | Ongoing Substation
144 | 1 | Port Harcourt | Installation of additional 1x60MVA,132/33kV transformer | Rumuosi |  | SLA | Substation Reinforcement
145 | 2 | Port Harcourt | Reinforcement with 1 x 100MVA 132/33kV Power Transformers. Outfitting of bay/ provison of additional 33kv breakers | Port Harcourt Main |  | WB/NETAP | Substation Reinforcement
146 | 3 | Port Harcourt | Reinforcement with 1 x 100MVA 132/33kV Power Transformers, | Port Harcourt Town |  | WB/NETAP | Substation Reinforcement
147 | 4 | Port Harcourt | Addition of 2nd 1 x60MVA, 132/33kV transformer | Elelenwo |  | SLA | Substation Reinforcement
148 | 5 | Port Harcourt | Reconstruction of Existing Double 132kV Line Circuit to 4 x 132kV Line Circuit Using the Same Right of Way from Afam to Port Harcourt Main (37.8km), and Creating Additional 3 x 132kV Line Bays at Afam and Port Harcourt Main TS | Port Harcourt Town |  | Tariff | Line Reconductoring
149 | 6 | Port Harcourt | Procurement of spare breakers, VTs, CTs, 33kv breakers, T-connectivity, transformer oil, etc at Port Harcourt Mains, Port Harcourt Town, Afaha Ube, Eket TS, Ekim TS, Calabar, Yenegoa TS |  |  | Tariff | Substation Reinforcement
150 | 7 | Port Harcourt | Construction of 132kv line from Abakiliki to Ikom and to Obudu | Abakaliki | Obudu | NDPHC | Ongoing Line
151 | 8 | Port Harcourt | Construction 132/33kv TS at Ikom | Ikom |  | NDPHC | Ongoing Substation
152 | 9 | Port Harcourt | Construction 132/33kv TS at Obudu | Obudu |  | NDPHC | Ongoing Substation
153 | 10 | Port Harcourt | Upgrade of existing 40MVA to 2x60MVA power transformers along with breakers and 33kV bays subject to handover to TCN | Rumuosi
154 | 11 | Port Harcourt | Completion and Commissioning of On-going TS at Ogoja | Ogoja |  | Tariff | Ongoing Substation
155 | 12 | Port Harcourt | Completion and commissioning 330kv line from Afam to Onne and 2x150MVA, 1x60MVA and 330/132kv TRX substation | Afam | Onne | NDPHC
156 | 13 | Port Harcourt | Construction of 2x330kV line bays extensions each at Delta and Port Harcourt substations | Delta | Port Harcourt | Tariff | Ongoing Line
157 | 14 | Port Harcourt | Construction of Delta-Port Harcourt 330kV DC line | Delta | Port Harcourt | Tariff | Ongoing Line
158 | 1 | Yola | Yola/Song/Little Gombi/Gulak/Mubi 132kV DC Line | Yola | Mubi | Tariff | Ongoing Line
159 | 2 | Yola | 2X60MVA,132/33kV TS | Mubi |  | Tariff | Ongoing Substation
160 | 3 | Yola | Uprating of 2X15MVA to 2X60MVA,132/33kV TS | Savanna |  | Tariff | Substation Reinforcement
161 | 4 | Yola | Molai/Bama 132kV DC Line | Molai | Bama | Tariff | New Line
162 | 5 | Yola | 2X60MVA,132/33kV TS | Bama |  |  | New Substation
163 | 6 | Yola | 132kV Terminal Equipment at Yola TS | Yola |  | Tariff | Substation Reinforcement
164 | 7 | Yola | Capacitors Banks, or other forms of FACTS compensation needed to improve our voltage profile in Borno state and environs | Molai TS and Baga Road Maiduguri |  | Tariff | Power Qaulity
165 | 8 | Yola | Upgrade and Reinforcement of 2X100MVA 132/33KV TS | Yola TS |  | WB/NETAP | Substation Reinforcement
166 | 9 | Yola | Additional 1X150MVA, 330/132KV TS | Yola TS |  | WB/NETAP | Substation Reinforcement
167 | 10 | Yola | 330/132KV TS 2X150MVA, 132/33KV 1X60MVA | Mayo Belwa TS |  | WB/NETAP | Substation Reinforcement
168 | 11 | Yola | Reinforcement of 132/33kV, 2X30MVA | Biu TS |  | WB/NETAP | Substation Reinforcement
169 | 12 | Yola | Upgrade with 1X150MVA 330/132kV 2X60MVA, 132/33kV TS | Molai TS |  | Tariff | Substation Reinforcement
170 | 13 | Yola | Reinforcement and complete rehabilitation with 2X60MVA, 132/33kV TS | Damboa TS |  | WB/NETAP | Substation Reinforcement
171 | 14 | Yola | Upgrade from 132/33kV TS to 330/132/33kV TS with 1X60MVA Mobitra 132/33kV TS | Jalingo TS |  | WB/NETAP | Substation Reinforcement
172 | 15 | Yola | Reinforcement with 2X60MVA 132/33kV TS | Potiskum TS |  | FGNPC | Substation Reinforcement
173 | 16 | Yola | 2X60MVA,132/33kV TS | Hong |  | Tariff | Ongoing Substation
174 | 17 | Yola | 2X60MVA,132/33kV TS | Song |  | Tariff | Ongoing Substation
175 | 18 | Yola | 2X60MVA,132/33kV TS | Little Gombi
Note on D108: Sulaimon Shittu: Project yet to be discussed with IE, more clarity required
Note on D110: Sulaimon Shittu: Project yet to be discussed with IE, more clarity required

## Abuja
S/N | Disco Rank | Disco | TCN Project Description | Station 1 | Station 2 | Finance Source | Type
1 | 1 | Abuja | Reconductoring of Katampe-Kubwa 132kV line | Katampe | Kubwa | Tariff | Line Reconductoring
2 | 2 | Abuja | Reconductoring of Apo-Karu-Keffi-Akwanga line | Apo | Akwanga | Tariff | Line Reconductoring
3 | 3 | Abuja | Reconductoring of Akwanga – Lafia Line | Akwanga | Lafia | Tariff | Line Reconductoring
4 | 4 | Abuja | Reconductoring of Lokoja - Obajana 330KV Line | Lokoja | Obajana | Tariff | Line Reconductoring
5 | 5 | Abuja | Reconductoring of Shiroro-Minna 132kV DC line | Shiroro | Minna | Tariff | Line Reconductoring
6 | 6 | Abuja | 30MVAr Capacitor Bank |  |  | Tariff | Power Qaulity
7 | 7 | Abuja | 50MX Reactor |  |  | Tariff | Power Qaulity

## Benin
S/N | Disco Rank | Disco | TCN Project Description | Station 1 | Station 2 | Finance Source | Type
8 | 1 | Benin | a. Replacement of the faulty 1x150MVA, 330/132kV Power Transformer b. Upgrading of 2x60MVA with 2x100MVA, 132kV/33kV, Power Transformers c. Construction of additional 2X33kV Feeder Bays | Asaba 132/33kv |  | SLA | Substation Reinforcement
9 | 2 | Benin | " Reinforcement with 1 x150MVA 330/132kV Power Transformers" Reinforcement with 1 x 100MVA 132/33KV Power Transformer Replacement of High Voltage Switchgears, and Associated Equipment. Replacement of Obsolete Control and Relay Panels with Digital Control System | Benin 330/132/33KV |  | WB/NETAP | Substation Reinforcement
10 | 3 | Benin | Upgrading of 2 x 30MVA with 2x 60MVA,132/33kV Power Transformers. o Replacement of High Voltage Switchgears, Control & Relay panel with Digital Control system and o Conversion of 6nos. 33kV Indoor to 8No Outdoor. Rehabilitation of control room | Ondo 132/33kv |  | WB/NETAP | Substation Reinforcement
11 | 4 | Benin | o Replacement of defective 1x 60MVA 132/33kV with a new 1x 1000MVA 132/33KV Power Transformer o Replacement High Voltage Switchgears, and Associated Equipment o Installation of 4 No Additional Feeder Bays at Effurun | Effurun 132/33kv |  | WB/NETAP | Substation Reinforcement
12 | 5 | Benin | Reconductoring of undersized conductor on the 132KV line between Ughelli and Effurun (10Km) | Ughelli | Effurun | SLA | Line Reconductoring
13 | 6 | Benin | Reconductoring of 132kV Oshogbo - Akure Single Circuit transmission line | Oshogbo | Akure | SLA | Line Reconductoring
14 | 7(a) | Benin | Construction of 2 numbers of additional 33kV Line Bays | Ihovbor 132/33KV |  | SLA | Substation Reinforcement
15 | 7(b) | Benin | Upgrade of 60MVA (T1) to 1 x 100MVA | Ihovbor 132/33KV |  | PPI Phase 1 | Substation Reinforcement
16 | 8 | Benin | 2 X 150MVA 330/132kV S/S and 2 X 60MVA 132/33kV substation, Akure | Akure 330/132/33KV |  | FGN/IGR | Ongoing Substation
17 | 9 | Benin | Construction and Installation of 2x60MVA, 132/33KV Substation at Ijesha-Isu with 6x132KV Line bays Extension/Switching station at Ado-Ekiti (Ikere) | Ijesha-Isu 132/33KV |  | FGN/IGR | Ongoing Substation
18 | 10 | Benin | Construction and Installation of 2x60MVA, 132/33KV Substation at Ilupeju and 2x132KV Line bays Extension at Ijesha-Isu | Ilupeju 132/33KV |  | FGN/IGR | Ongoing Substation
19 | 11 | Benin | Construction of 1 x 60MVA, 132/33kV Substation at Kwale | Kwale 132/33KV |  | FGN/IGR | Ongoing Substation
20 | 12 | Benin | Construction of Ado-Ekiti (Ikere)-Ijesha Isu 132kV Double Circuit Transmission Line | Ado Ekiti 132/33KV | Ijesa Isu 132/33KV | FGN/IGR | Ongoing Substation
21 | 13 | Benin | 2x 150MVA 330/132KV substation at Omotosho | Omotosho 132/33KV |  | FGN/IGR | Ongoing Substation
22 | 14 | Benin | 2x60MVA 132/33kV substation at Okeagbe, Ondo State and line bays extension at Obajana | Okeagbe 132/33KV |  | FGN/IGR | Ongoing Substation
23 | 15 | Benin | 2x60MVA, 132/33kV Substation at Ose LGA Headquarters, Ondo State | Ose 132/33KV |  | FGN/IGR | Ongoing Substation
24 | 16 | Benin | Construction of Ijesha-Isu - llupeju 132kV Double Circuit Transmission Line | Ijesha-Isu 132/33KV | Ilupeju 132/33KV | FGN/IGR | New Line
25 | 17 | Benin | Construction of 2x60MVA, 132/33KV Substation at Ikare-Akoko and 2x132KV Line bays Extension at Okeagbe | Ikare-Akoko 132/33KV |  | FGN/IGR | Ongoing Substation
26 | 18 | Benin | Construction of 132kV Okeagbe-Ikare-Akoko Double Circuit Transmission Line (15km) | Okeagbe 132/33KV | Ikare-Akoko 132/33KV | FGN/IGR | New Line
27 | 19 | Benin | a. Replacement of 3No 132kV and 9Nos 33kV Current transformers and b. Differential relay at Oghara 132kV TS to restore the standby 30MVA power transformer | Oghara 132/33KV |  | SLA | Substation Reinforcement
28 | 20 | Benin | Upgrading of faulty 1x30MVA, 132/33kV Transformer with 1x60MVA power transformer | Afisere 132/33kV |  | SLA | Substation Reinforcement
29 | 21 | Benin | a. Replacement of faulty grounding on 1x40MVA, 132/33kV. b. Replacement of differential relay and surge Arrester on 1x40MVA transformer. | Okada 132/33KV |  | SLA | Substation Reinforcement
30 | 22 | Benin | Reconstruction of one of Delta-Benin 330kV Transmission Line (107 km) Double Circuit to Quad Conductor 330 Double Circuit Line | Delta 330/132/33KV | Benin 330/132/33KV | AFDB/NTEP | Line Reconstruction
31 | 23 | Benin | Construction of new Double Circuit (DC) 132kV Okada-Gilli-Gilli | Okada 132/33KV | Gilli-Gilli 132/33KV | AFDB/NTEP | New Line
32 | 24 | Benin | Construction of new DC Transmission Line 132kV Sapele - Odilli DC Transmission Line | Sapele 132/33KV | Odilli 132/33KV | AFDB/NTEP | New Line
33 | 25 | Benin | Upgrade of 30MVA (T1) to 1 x 60MVA | Amukpe 132/33KV |  | PPI Phase 1 | Substation Reinforcement
34 | 26 | Benin | Reconductoring of Irrua- Okpilai 132kV line (43km) with Turn In- Turn Out Tower at Okpila 132kV Substation. | Irrua 132/33KV | Okpilla 132/33KV | Reconductoring | Line Reconductoring
35 | 27 | Benin | a) 2X60 MVA,132/33kV transformers 6 X 33kV feeder bay | Gilli-Gilli 132/33KV |  | AFDB/NTEP | New Substation
36 | 28 | Benin | Construction of 1 x 150MVA, 330/132kV Substation at Okpai | Okpai 132 |  | FGN/IGR | Ongoing Substation
37 | 30 | Benin | Construction of 132kV Okpai-Kwale DC Transmission Line | Okpai 132/33KV | Kwale 132/33KV | FGN/IGR | New Line
38 | 31 | Benin | Reconductoring of Irrua - Benin 132kV line (81km) with Turn In- Turn Out Tower at Irrua 132kV Substation. | Irrua 132/33KV | Benin 132/33KV | Reconductoring | Line Reconductoring
39 | 32 | Benin | Reinforcement with 1 x 100MVA 132/33KV Power Transformer | Delta 330/132/33KV |  | WB/NETAP | Substation Reinforcement
40 | 33 | Benin | Supply and installation of 100MVA 132/33KV power Transformer and associated Switchgears at | Irrua 132/33KV |  | WB/NETAP | Substation Reinforcement
41 | 34 | Benin | Reinforcement with 1 x 150MVA 330/132kV Interbus Transformer, | Delta 330/132/33KV |  | WB/NETAP | Substation Reinforcement
42 | 35 | Benin | Replacement of High Voltage Switchgears, and Associated Equipment. Replacement of Obsolete Control and Relay Panels with Digital Control System | Effurun 132/33KV |  | WB/NETAP | Substation Reinforcement
43 | 36 | Benin | Construction of complete new 132/33kV Substation at Gilli-Gilli | Gilli-Gilli 132/33KV |  | AFDB/NTEP | New Substation
44 | 37 | Benin | Transformers Spares: Power Transformers (2x150MVA) | TCN |  | SLA | SLA Equipment
45 | 38 | Benin | Transformers Spares: Power Transformers (2x100MVA) | TCN |  | SLA | SLA Equipment
46 | 39 | Benin | Transformers Spares: Power Transformers (2x60MVA) | TCN |  | SLA | SLA Equipment
47 | 40 | Benin | 1 x 60 MVA Mobile Substations | TCN |  | SLA | SLA Equipment

## Eko
S/N | Disco Rank | Disco | TCN Project Description | Station 1 | Station 2 | Finance Source | Type
48 | 1 | Eko | Omotosho-Epe DC Line | Omotosho | Epe | Tariff | Ongoing Line
49 | 2 | Eko | Construction of 2X150MVA, 330/132kV and 2X60 MVA, 132/33kV substations at Epe | Epe |  | Tariff | New Substation
50 | 3 | Eko | Construction of 2X150MVA, 330/132kV and 2X60 MVA, 132/33kV substations fully equipped | Lekki FTZ |  | Tariff | New Substation
51 | 4 | Eko | Epe - Lekki EPZ(25km) 330kv Double Circuit Transmission Line | Epe | Lekki FTZ | Tariff | New Line
52 | 5 | Eko | 132 kV DC line from Epe TS to Eleko Junction TS | Epe | Eleko Junction TS | Tariff | Proposed Line
53 | 6 | Eko | Construction of 2 X 60MVA 132/33kV Substation at Eleko TS | Election Junction |  | Tariff | Proposed Substation
54 | 7 | Eko | 132 kV DC line from Epe TS to Oko--Abe TS | Epe | Oko Abe | Tariff | New Line
55 | 8 | Eko | Construction of 2 X 60MVA 132/33kV Substation at Oko-Abe | Oko Abe |  | Tariff | New Substation
56 | 9 | Eko | Construction of 12.5km of new 330kV double circuit line from new Ejio 330/132/33kV substation to Olorunsogo 330kV switchyard inclusive of 1.5km 2x 330KV DC multi circuits line | Ejio | Olorunshogo | JICA | New Line
57 | 10 | Eko | Construction of 29.6km of new 330kV double circuit line from new Ejio 330/132/33kV substation to Ajegunle (New Agbara) 330/132/33kV substation | Ejio | New Agabra | JICA | New Line
58 | 11 | Eko | Construction of 36.2km of new 132kV double circuit line from New Agbara (Ajegunle) 330/132/33kV substation to the proposed Badagary 132/33kV substation. | New Agbara | Badagry | JICA | New Line
59 | 12 | Eko | Construction of complete new 330/132/33kV AIS substation at Ajegunle (New Agbara) | New Agbara |  | JICA | New Substation
60 | 13 | Eko | Construction of 2 X 60MVA 132/33kV substation at Badagary | Badagary |  | JICA | New Substation

## Enugu
S/N | Disco Rank | Disco | TCN Project Description | Station 1 | Station 2 | Finance Source | Type
61 | 1 | Enugu | Construction of 2x60 MVA 132kV substation Nnewi | Nnewi |  | Tariff | Ongoing Substation
62 | 2 | Enugu | Completion of Nnewi 2x60MVA Transmission project and 132kV Onitsha-Nnewi line. (to reduce Feeder length of 189.96km) | Nnewi | Onitsha | Tariff | Ongoing Line
63 | 3 | Enugu | Complete Installation of 100MVA, 132/33KV.GCM Onitsha | Onitsha |  | Tariff | Ongoing Substation
64 | 4 | Enugu | 2X60MVA,132/33kV transformers,NINTH MILES | Ninth Mile |  | Tariff | Ongoing Substation
65 | 5 | Enugu | Complete installation of 1 x 60MVA, 132/33kV Transformer OJI o (to stop Load sheddding on Udi, Achi, Oji-Urban and Orumba 33kV Feeders) | Oji |  | Tariff | Ongoing Substation
66 | 6 | Enugu | Construction/Completion of Arochukwu 1 X 40MVA. | Arochukwu |  | Tariff | Ongoing Substation
67 | 7 | Enugu | Construction /Completion of Orlu 2 X 60MVA. (to reduce Orlu Feeder length of 265.22km and improve supply to Orlu and Akokwa) | Orlu |  | Tariff | Ongoing Substation
68 | 8 | Enugu | Upgrading of 330kV Onitsha - Enugu Transmission Line | Enugu |  | Tariff | Ongoing Substation
69 | 9 | Enugu | Construction/Completion of Okigwe 2 X 60MVA T/S. (to reduce Okigwe Feeder length of 399.37km and improve supply to Okigwe, Mbaise and Orlu) | Okigwa |  | Tariff | Ongoing Substation
70 | 10 | Enugu | o Construction of 2x60MVA, 132/33kV substation at Amasiri, Afikpo | Amasiri |  | Tariff | Ongoing Substation
71 | 11 | Enugu | Completion of Installation of 1 X 60MVA Power TRF in Nibo . (to reduce Agulu Feeder length of 220.29km and Neni Feeder length of 113.44km) | Nibo |  | Tariff | Ongoing Substation
72 | 12 | Enugu | Completion of the 2 X60MVA Project.Abor Mbaise | Abor Mbaise |  | Tariff | Ongoing Substation
73 | 13 | Enugu | Installation of 2 X 60MVA at Egbu and replacement of bad 33KV Breakers. (to reduce Airport Feeder length of 180.26km and improve supply to Ngo-Okpala) | Egbu |  | Tariff | Ongoing Substation
74 | 14 | Enugu | o Construction of 2x60MVA, 132/33kV substation at Ideato | Ideato |  | Tariff | Ongoing Substation
75 | 15 | Enugu | Construction of 2x30/40MVA 132/33kV substation MBALANO | Mbalano |  | Tariff | Ongoing Substation
76 | 16 | Enugu | Construction of 2x60MVA, 132/33kV substation NENWE | Nnewe |  | Tariff | Ongoing Substation
77 | 17 | Enugu | o Construction of 2x60MVA, 132/33kV substation UMUCHU,IBUGHUBU | Umuchu, Ibughubu |  | Tariff | Ongoing Substation
78 | 18 | Enugu | Construction of 2x60MVA, 132/33kV Substation ,AGULERI | Aguleri |  | Tariff | Ongoing Substation
79 | 19 | Enugu | Construction of 2x60MVA, 132/33kV substation at Ifitedunu and 2x132kV line bays extension at Onitsha. | Onitsha |  | Tariff | Ongoing Substation

## Ibadan
S/N | Disco Rank | Disco | TCN Project Description | Station 1 | Station 2 | Finance Source | Type
80 | 1 | Ibadan | Uprating and Dualization of the Ayede-Sagamu-Ijebu ode 132KV line . | Ayede | Ijebu Ode | Tariff | Line Reconstruction
81 | 2 | Ibadan | Installation of additional 100MVA, 132/33kV transformer at Ibadan North 330kV/132kV/33kV TS | Ibadan North |  | Tariff | Substation Reinforcement
82 | 3 | Ibadan | Reconductoring of Eleyele to Ibadan North 132Kv line | Eleyele | Ibadan North | Tariff | Line Reconductoring
83 | 4 | Ibadan | Upgrading of 1x40MVA & 1x45MVA Mobitra to 1x100MVA, 132/33kV & 40MVA,132/33KVTransformer including 2x33kV feeder bays at Jericho 132 | Jericho |  | Tariff | Substation Reinforcement
84 | 5 | Ibadan | Replacement of faulty 60MVA,132/33kV, Transformer at Ijebu-ode TS | Ijebu Ode |  | Tariff | Substation Reinforcement
85 | 6 | Ibadan | Completion of 100MVA,132/33kV upgrade at Ota TS | Ota |  | Tariff | Substation Reinforcement
86 | 7 | Ibadan | Upgrading of Iwo 1 x 40MVA, 132/33kV to 60MVA, 132/33kV Transformer | Iwo |  | Tariff | Substation Reinforcement
87 | 8 | Ibadan | Construction of 1x60MVA,132/33kV Ayede 132 to Eleyele 132kV | Eleyele |  | FGNPC | Ongoing Substation
88 | 9 | Ibadan | Construction of 2x60MVA 132/33KV Substation at Interchange 132kV | Sagamu Interchange |  | Tariff | Proposed Substation
89 | 10 | Ibadan | Installation of additional 60MVA, 132/33kV transformer at Ganmo 330/132/33kV Ts | Ganmo |  | Tariff | Substation Reinforcement
90 | 11 | Ibadan | Construction of 2 x 60MVA 132/33kV Substation at Ogbomosho 132kV | Ogbomosho |  | Tariff | Ongoing Substation
91 | 12 | Ibadan | Installation of 1x 60MVA at Ile-Ife 132kV/33kV TS | Ile-Ife |  | Tariff | Substation Reinforcement
92 | 13 | Ibadan | Construction of complete new 1x150MVA, 330/132kV with 2x60MVA, 132/33kV at Asejire | Asejire |  | Tariff | Ongoing Substation
93 | 14 | Ibadan | Construction of 1x60MVA 132/33KV Substation at Sapaade 132kV | Sapaade |  | Tariff | Ongoing Substation
94 | 15 | Ibadan | Construction of complete new 330/132/33kV AIS substation at Likosi (Ogijo) at Likosi 330/132/33 | Likosi |  | JICA | New Substation
95 | 16 | Ibadan | Construction of complete new 330/132/33kV AIS substation at Ejio (Arigbajo) at Ejio 330/132/33 | Ejio |  | JICA | New Substation
96 | 17 | Ibadan | Construction of complete new 330/132/33kV AIS substation at Ajegunle (New Agbara) 330/132/33 | New Agbara |  | JICA | New Substation

## Ikeja
S/N | Disco Rank | Disco | TCN Project Description | Station 1 | Station 2 | Finance Source | Type
97 | 1 | Ikeja | Upgrade of Ikeja West-Alimosho-Ogba(-Alausa)-Otta-Papalanto Ring | Ikeja West | Otta | Tariff | Line Reconductoring
98 | 2 | Ikeja | Reinforcement with addition of 1 x 100MVA 132/33kV Power Transformer at Alausa TS | Alausa |  | Tariff | Substation Reinforcement
99 | 3 | Ikeja | Upgrading of T1 30MVA To 60MVA transformer at Itire TS | Itire |  | Tariff | Substation Reinforcement
100 | 4 | Ikeja | Completion of conversion of 33kV indoor breaker to outdoor breaker at Akoka TS | Akoka |  | Tariff | Substation Reinforcement
101 | 5 | Ikeja | Upgrade 30MVA to 100MVA at Maryland TS | Maryland |  | Tariff | Substation Reinforcement
102 | 6 | Ikeja | Upgrading of 2 x 30MVA transformer to 2 X 60MVA transformer at Amuwo TS | Amuwo |  | Tariff | Substation Reinforcement
103 | 7 | Ikeja | Reinforcement with addition of 1 x 60MVA 132/33kV Power Transformer at Oke Aro TS TS | Oke Aro |  | Tariff | Substation Reinforcement
104 | 8 | Ikeja | Upgrading of 45MVA transformer 60MVA at Isolo TS | Isolo |  | Tariff | Substation Reinforcement
105 | 9 | Ikeja | Construction of Additional Bays at Ejigbo TS | Ejigbo |  | Tariff | Substation Reinforcement
106 | 10 | Ikeja | Construction of Additional Bays at Ogba TS | Ogba |  | Tariff | Substation Reinforcement
107 | 11 | Ikeja | Upgrade of Egbin-Ikorodu line | Egbin | Ikorodu | Tariff | Line Reconductoring
108 | 12 | Ikeja | Reinforcement with addition of 1 x 60MVA 132/33kV Power Transformer at Oworo TS | Oworo |  | Tariff | Substation Reinforcement
109 | 13 | Ikeja | Upgrade of Akangba-Isolo line | Akangba | Isolo | Tariff | Line Reconductoring
110 | 14 | Ikeja | 132kV Multi-Circuit Oke Aro to Alausa Transmission Line | Oke Aro | Alausa | NPDHC | Ongoing Line
111 | 15 | Ikeja | Propose KARA/BERGER 132/33kV Station. | Kara/berger |  | Tariff | Proposed Substation
Note on D12: Sulaimon Shittu: Project yet to be discussed with IE, more clarity required
Note on D14: Sulaimon Shittu: Project yet to be discussed with IE, more clarity required

## Jos
S/N | Disco Rank | Disco | TCN Project Description | Station 1 | Station 2 | Finance Source | Type
112 | 1 | Jos | Completion of Transposition on the Uguaji-Jos 330kV line | Ugwuaji | Jos | Tariff | Existing
113 | 2 | Jos | Construction of the Makeri-Pankshin 132KV DC Line. | Makeri | Pankshin | Tariff | Ongoing Line
114 | 3 | Jos | Construction of complete new 132/33kV substation at Biliri | Biliri |  | WB/NETAP | Ongoing Substation
115 | 4 | Jos | Construction of complete new 330/132/33kV Substation at Bauchi by turning in and turning out of the existing 330kV Single Circuit Jos-Gombe line at Bauchi | Bauchi |  | AFD NOR CORR | New Substation
116 | 5 | Jos | Construction of the Alkaleri 132/33kV substation | Alkaleri |  | Tariff | Proposed Substation
117 | 6 | Jos | Construction of the Misau 132/33kV substation | Misau |  | Tariff | Proposed Substation

## Kaduna
S/N | Disco Rank | Disco | TCN Project Description | Station 1 | Station 2 | Finance Source | Type
118 | 1 | Kaduna | Construction of complete new 330/132/33kV Substation at Millennium City, Kaduna by turning in and turning out of the existing 330kV DC Kaduna Jos line at Millennium City, | Millennium City |  | AFDB/NTEP | New Substation
119 | 2 | Kaduna | Construction of complete new 330/132/33kV Substation at New Sokoto | Sokoto |  | AFD NOR CORR | New Substation
120 | 3 | Kaduna | Installation of 1x60 MVA, 132/33kV power transformer at Sokoto 132/33kV TS | Sokoto |  | SLA | Substation Reinforcement
121 | 4 | Kaduna | Construction of complete new 132/33kV Substation at Rigasa by turning in and turning out of the existing 132kV DC Kaduna Zaria line at Rigasa | Rigasa |  | AFDB/NTEP | New Substation
122 | 5 | Kaduna | Construction of complete new 330/132/33kV Substation at Zaria by turning in and turning out of the existing 330kV SC Kaduna Kano line at Zaria, | Zaria |  | AFDB/NTEP | New Substation
123 | 6 | Kaduna | Upgrading Of Existing 90MVA at Birnin Kebbi TS | Birnin Kebbi |  | WB/NETAP | Substation Reinforcement
124 | 7 | Kaduna | Construction of complete new 132/33kV Substation at Jaji by turning in and turning out of the existing 132kV DC Kaduna - Zaria line at Jaji | Jaji |  | AFDB/NTEP | New Substation
125 | 8 | Kaduna | Upgrading of 1x30 MVA to 1x60 MVA, 132/33kV Transformer at Gusau 132/33kV TS | Gusau |  | SLA | Substation Reinforcement
126 | 9 | Kaduna | Construction and installation of 1x45MVA Mobitra 132/33kV down dropper (on existing B/Kebbi-Sokoto 132kV S/C transmission line) TS at Argungu | Argungu |  | SLA | New Substation
127 | 10 | Kaduna | Installation of 1X150MVA 330/132/33kV transformer at Mando TS | Mando |  | Tariff | Substation Reinforcement
128 | 11 | Kaduna | Additional 132/33kv Transmission Station At Eastern Byepass Kaduna To Take Care Of The Growing Expansion In The Region | Eastern ByePass (Kaduna) |  | Tariff | Proposed Substation
129 | 12 | Kaduna | Construction of new substation at New Industrial Zone along Kaduna – Abuja express way | New Industrial Zone (Kaduna Abuja Express Way) |  | Tariff | Proposed Substation
130 | 13 | Kaduna | Construction and Installation of 2x60MVA, 132/33KV Substation at Kafanchan with 2x132KV Linebays at Jos | Kafanchan |  | Tariff | Ongoing Substation
131 | 14 | Kaduna | Construction of complete new 330/132/33kV Substation at Kalgo | Kalgo |  | AFD NOR CORR | New Substation

## Kano
S/N | Disco Rank | Disco | TCN Project Description | Station 1 | Station 2 | Finance Source | Type
132 | 1 | Kano | Mando - Kumbotso 2nd 330kV Line | Mando | Kumbotso | AFDB/NTEP | New Line
133 | 2 | Kano | Walalambe 132KV | Walalambe |  | Tariff | New Substation
134 | 3 | Kano | Jogana 330kV | Jogana |  | AFD NOR CORR | New Substation
135 | 4 | Kano | Reconductoring of Kumbotso - Dakata 132kV line | Kumbotoso | Dakata | Tariff | Line Reconductoring
136 | 5 | Kano | Reconstruction of Kano - Dan Agundi 132kV single circuit transmission line | Kumbotoso | Dan Agudi | Tariff | Line Reconductoring
137 | 6 | Kano | Refurbishment of all 132kV sub-stations existing capacitor Banks and installation of additional ones in stations where there is non within KEDCO operational area for power quality |  |  | Tariff | Power Qaulity
138 | 7 | Kano | Rimin Zakara 330KV | Rimin Zakara |  | WB/NETAP | Ongoing Substation
139 | 8 | Kano | Reconductoring of Kumbotso - Hadeija | Kumbotoso | Hadeija | Tariff | Line Reconductoring
140 | 9 | Kano | Dan- Gwauro 2x60MVA, 132/33kV | Dan-Gwauro |  | Tariff | Proposed Substation
141 | 10 | Kano | Dawanau 2x60MVA, 132/33kV | Dawanau |  | Tariff | Proposed Substation
142 | 11 | Kano | Bela/Tagurza 2x60MVA, 132/33kV TS | Bela/Tagurza |  | Tariff | Proposed Substation
143 | 12 | Kano | Katsina 330KV | Katsina |  | Tariff | Ongoing Substation

## Port Harcourt
S/N | Disco Rank | Disco | TCN Project Description | Station 1 | Station 2 | Finance Source | Type
144 | 1 | Port Harcourt | Installation of additional 1x60MVA,132/33kV transformer | Rumuosi |  | SLA | Substation Reinforcement
145 | 2 | Port Harcourt | Reinforcement with 1 x 100MVA 132/33kV Power Transformers. Outfitting of bay/ provison of additional 33kv breakers | Port Harcourt Main |  | WB/NETAP | Substation Reinforcement
146 | 3 | Port Harcourt | Reinforcement with 1 x 100MVA 132/33kV Power Transformers, | Port Harcourt Town |  | WB/NETAP | Substation Reinforcement
147 | 4 | Port Harcourt | Addition of 2nd 1 x60MVA, 132/33kV transformer | Elelenwo |  | SLA | Substation Reinforcement
148 | 5 | Port Harcourt | Reconstruction of Existing Double 132kV Line Circuit to 4 x 132kV Line Circuit Using the Same Right of Way from Afam to Port Harcourt Main (37.8km), and Creating Additional 3 x 132kV Line Bays at Afam and Port Harcourt Main TS | Port Harcourt Town |  | Tariff | Line Reconductoring
149 | 6 | Port Harcourt | Procurement of spare breakers, VTs, CTs, 33kv breakers, T-connectivity, transformer oil, etc at Port Harcourt Mains, Port Harcourt Town, Afaha Ube, Eket TS, Ekim TS, Calabar, Yenegoa TS |  |  | Tariff | Substation Reinforcement
150 | 7 | Port Harcourt | Construction of 132kv line from Abakiliki to Ikom and to Obudu | Abakaliki | Obudu | NDPHC | Ongoing Line
151 | 8 | Port Harcourt | Construction 132/33kv TS at Ikom | Ikom |  | NDPHC | Ongoing Substation
152 | 9 | Port Harcourt | Construction 132/33kv TS at Obudu | Obudu |  | NDPHC | Ongoing Substation
153 | 10 | Port Harcourt | Upgrade of existing 40MVA to 2x60MVA power transformers along with breakers and 33kV bays subject to handover to TCN | Rumuosi
154 | 11 | Port Harcourt | Completion and Commissioning of On-going TS at Ogoja | Ogoja |  | Tariff | Ongoing Substation
155 | 12 | Port Harcourt | Completion and commissioning 330kv line from Afam to Onne and 2x150MVA, 1x60MVA and 330/132kv TRX substation | Afam | Onne | NDPHC
156 | 13 | Port Harcourt | Construction of 2x330kV line bays extensions each at Delta and Port Harcourt substations | Delta | Port Harcourt | Tariff | Ongoing Line
157 | 14 | Port Harcourt | Construction of Delta-Port Harcourt 330kV DC line | Delta | Port Harcourt | Tariff | Ongoing Line

## Yola
S/N | Disco Rank | Disco | TCN Project Description | Station 1 | Station 2 | Finance Source | Type
158 | 1 | Yola | Yola/Song/Little Gombi/Gulak/Mubi 132kV DC Line | Yola | Mubi | Tariff | Ongoing Line
159 | 2 | Yola | 2X60MVA,132/33kV TS | Mubi |  | Tariff | Ongoing Substation
160 | 3 | Yola | Uprating of 2X15MVA to 2X60MVA,132/33kV TS | Savanna |  | Tariff | Substation Reinforcement
161 | 4 | Yola | Molai/Bama 132kV DC Line | Molai | Bama | Tariff | New Line
162 | 5 | Yola | 2X60MVA,132/33kV TS | Bama |  |  | New Substation
163 | 6 | Yola | 132kV Terminal Equipment at Yola TS | Yola |  | Tariff | Substation Reinforcement
164 | 7 | Yola | Capacitors Banks, or other forms of FACTS compensation needed to improve our voltage profile in Borno state and environs | Molai TS and Baga Road Maiduguri |  | Tariff | Power Qaulity
165 | 8 | Yola | Upgrade and Reinforcement of 2X100MVA 132/33KV TS | Yola TS |  | WB/NETAP | Substation Reinforcement
166 | 9 | Yola | Additional 1X150MVA, 330/132KV TS | Yola TS |  | WB/NETAP | Substation Reinforcement
167 | 10 | Yola | 330/132KV TS 2X150MVA, 132/33KV 1X60MVA | Mayo Belwa TS |  | WB/NETAP | Substation Reinforcement
168 | 11 | Yola | Reinforcement of 132/33kV, 2X30MVA | Biu TS |  | WB/NETAP | Substation Reinforcement
169 | 12 | Yola | Upgrade with 1X150MVA 330/132kV 2X60MVA, 132/33kV TS | Molai TS |  | Tariff | Substation Reinforcement
170 | 13 | Yola | Reinforcement and complete rehabilitation with 2X60MVA, 132/33kV TS | Damboa TS |  | WB/NETAP | Substation Reinforcement
171 | 14 | Yola | Upgrade from 132/33kV TS to 330/132/33kV TS with 1X60MVA Mobitra 132/33kV TS | Jalingo TS |  | WB/NETAP | Substation Reinforcement
172 | 15 | Yola | Reinforcement with 2X60MVA 132/33kV TS | Potiskum TS |  | FGNPC | Substation Reinforcement
173 | 16 | Yola | 2X60MVA,132/33kV TS | Hong |  | Tariff | Ongoing Substation
174 | 17 | Yola | 2X60MVA,132/33kV TS | Song |  | Tariff | Ongoing Substation
175 | 18 | Yola | 2X60MVA,132/33kV TS | Little Gombi