SCHEDULE 5

#### APPLICATION PROCEEDINGS AND TIMELINES FOR REGISTRATION AND MINI-GRID PERMIT

These proceedings for a permit or a Tripartite Agreement shall guide the mini-grid developers to make use of the Mini-Grid Regulation (the “Regulations”) 2026. The proceedings shall not replace the Regulations. Where there is any conflict between the Regulations and this document, the Regulations shall prevail.

- KEY CONSIDERATIONS

To apply for a permit or the registration of a Tripartite Agreement, the process differs if the main grid is already present in the area where the project will be developed or the site is off-grid.

Where an area has no existing distribution grid, the area is considered as unserved and may receive an Isolated mini-grid.

Where the grid is present, but the area is poorly electrified or has a non-functional distribution-grid, it is considered as underserved and is eligible for an interconnected mini-grid.

- UNSERVED AREAS – ISOLATED MINI-GRIDS

The entire application process for unserved areas is summarised in the figure 1 (left part) and 2 located at the end of this document. In these figures, the steps are described from the point of view of the mini-grid developer.

##### STEP 1: IDENTIFICATION OF THE ELIGIBILITY OF UNSERVED AREA

To be eligible, the area selected must meet the following conditions:

- The area is unserved.

- The area must not have been assigned to an IEDNO or any other mini-grid developer.

- The area is not part of an already existing expansion plan (5-year plan) of a Distribution licensee.

Where it is identified that the area is part of an expansion plan of a Distribution licensee , the mini-grid developer needs the consent of the Distribution licensee  before the area identified becomes eligible.

If the area identified fulfils all the requirements listed above, the process can continue and the contact with the Community can be established.

As a repository of the expansion plans of the Distribution licensee s and applications from IEDNOs and other mini-grid developers, THE COMMISSION may also assist mini-grid developers in identifying a suitable area that fulfils the above-mentioned criteria. Federal and State authorities responsible for electrification should also be consulted.

##### STEP 2: CONTACT WITH THE COMMUNITY AND SETTLEMENT OF AN EXCLUSIVITY PERIOD

Now that the area located can potentially receive an isolated mini-grid, the community concerned should be contacted to know whether the local population is interested in benefiting from the services provided by the mini-grid operator. The community or the mini-grid developer can approach the other party to start negotiations. At that stage, the community and the mini-grid developer can decide to set an exclusivity period.

This exclusivity period is used to investigate the feasibility of implementing a mini-grid at the location and ensures that no other operator is conducting any other feasibility during the investigation period.

The exclusivity period is an agreement only between the community and the mini-grid operator and is only valid up to 12 months. This period could then be extended once and only for a further 12 months subject to the approval of the Commission. In all cases, the executed Exclusivity Agreements must be submitted to the Commission.

If at the inception, the mini-grid operator needs an exclusivity period of more than 12 months, it can also enter into an exclusivity agreement. However, this would need to be justified, submitted to the Commission and the agreement approved by the Commission.

The Schedule 1A of the Regulations (called “Agreement for exclusivity period”) provides a form that shall be used to draft the exclusivity agreement.

##### STEP 3: SIZE OF THE SYSTEM AND REGISTRATION

If the power distributed by the Isolated mini-grid is larger than 100 kW, the mini-grid developer shall apply for a mandatory mini-grid Permit. If the installed generation capacity of the power station is larger than 5 MW, the plant shall not qualify as an isolated mini-grid under the Mini Grid Regulations 2026. Portfolio applications for isolated mini-grids may be submitted in accordance with section 10 of the Mini Grid Regulations 2026, provided the sites are within the same regulatory jurisdiction. Generation capacity is the guaranteed active power that a generation plant can supply to a load or network under the applicable environmental conditions and a power factor of 0.8 (inductive) for at least one hour, assuming the plant is well maintained and fully functional.

If the power distributed by the isolated mini-grid is below 100kW, the mini-grid developer can voluntarily apply for a permit following the same procedure as for the mandatory permit.

A distribution network distributes a power up to 100kW if the average active power fed into the distribution network in each 15 min interval of its operation period is below or equal to 100kW.

In case it is granted with the permit by the Commission, the mini-grid permit holder will be entitled to receive a compensation before the mini-grid can be connected to the main distribution grid and will enjoy any other protection given to the mini-grid under the Regulations.

The mini-grid operator that has been granted a mini-grid permit will need to establish an agreement with the beneficiary community. The Mini-Grid Operators may decide to use the template included in Schedule 11.

In case the mini-grid developer decides not to apply for a mini-grid permit, it shall register by submitting the registration form called as in Schedule 2 of the Mini Grid Regulations 2026).

- UNDERSERVED AREAS – INTERCONNECTED MINI-GRIDS

The entire application process for underserved areas is summarised in the figure 1 (right part) and 3 located at the end of this document. In these figures, the steps are described from the point of view of the mini-grid developer/operator.

##### STEP 1: IDENTIFICATION OF THE ELIGIBILITY OF AN UNDERSERVED AREA

To be eligible, the community concerned should be first contacted in order to know whether the local population is interested in benefitting from the services provided by the mini-grid operator. The community selected should meet the following criteria -

- The community is being underserved. The main grid is present in that area, but does not provide a sufficient level of service to meet the community’s electricity demand.

- The community is ready to pay higher tariffs than the main grid tariff to improve the reliability of electricity supply.

##### STEP 2: CONTRACT WITH THE DISTRIBUTION LICENSEE AND SETTLEMENT OF AN EXCLUSIVITY PERIOD

Once it has been established that the area located can potentially receive an interconnected mini-grid, the Distribution licensee should be contacted to know if it would be willing to enter in a Tripartite Agreement (refer to Schedule 10 for a proposed template).

At that stage, the community, the mini-grid developer and the Distribution licensee  can decide to set an exclusivity period.

This exclusivity period is used to investigate the feasibility of implementing a mini-grid at the location and ensures that no other operator is conducting any other feasibility study during the investigation period.

The exclusivity period is an agreement between the community, the mini-grid developer and the Distribution licensee valid for up to 12 months. However, this period can be extended once and only for a further 12 months subject to the approval of the Commission (refer to Schedule 1B). In all cases, the executed Exclusivity Agreements must be submitted to the Commission.

If at the inception, the mini-grid developer needs an exclusivity period of more than 12 months, it can also enter into an exclusivity agreement. However, this would need to be justified to the Commission and the agreement approved by the Commission.

Schedule 1B of the Regulations (called “Agreement for exclusivity period for Interconnected mini-grid”) is the document to use to set an exclusivity period.

##### STEP 3: TRIPARTITE AGREEMENT AND REGISTRATION

An agreement between the connected community, the mini-grid operator and the Distribution licensee must be reached and a Tripartite Agreement (Schedule 10 of the Mini Grid Regulations 2026) must be established.

The contract is then submitted to THE COMMISSION for approval and the issuance of a mini-grid permit. Multiple Tripartite Agreements for a portfolio of interconnected mini-grids within the same regulatory jurisdiction and with Tripartite Agreements having been executed with the same Distribution Licensee may be submitted simultaneously in accordance with section 10 of the Mini Grid Regulations 2026.

APPLICATION PROCESS FOR A MINI-GRID PERMIT PURSUANT TO REGULATIONS 7, 8 & 9

- Form of Application

- In case of a mini-grid permit, the application shall be in the form specified in Schedule 3 and shall contain the information specified therein. In case of an interconnected mini-grid, the mini-grid developer shall submit the Tripartite Agreement, as agreed with the Distribution licensee and the beneficiary community, for approval.

- The application shall submit via the Commission’s Online Application Portal.

- The application shall be signed and dated by the applicant or authorised representative of the applicant.

- The applications for the mini-grid permit or approval of the Tripartite Agreement and granting of a mini-grid permit must contain all the information specified in the Application form or the contract respectively.

###### 2. Acknowledgement of the Application

On receipt of the Application, the Commission shall note thereon the date of its receipt and shall send to the Applicant an acknowledgement stating the date of receipt.

###### 3. Approval or Refusal of mini-grid Permit

After due consideration of the Application, the Commission shall issue or refuse the issuance of the mini-grid Permit.

- The period between the acknowledgement of receipt of the application as specified in Paragraph 2, and the date on which the Commission notifies the Applicant of its decision or proposed decision to approve or refuse the permit, shall not exceed (30) thirty days.

- Where the Commission has approved a permit, the Commission shall inform the Applicant of such approval and the conditions to be satisfied before the grant of the permit.

- If the Commission intends to refuse the issuance of a permit, it shall notify the Applicant in writing of its intention stating the reasons for the decision.

- The Applicant shall have the opportunity to make adequate representations to the Commission within (30) thirty days of the Applicant’s receipt of the notification from the Commission of the refusal of a permit.

- The Commission shall consider the representation made by the Applicant and shall, if the representation is unsuccessful, or no representation was made, duly notify the Applicant in writing that the Application for a permit has been refused.

- The reasons for refusing the permit shall be clearly stated in writing by the Commission to the Applicant

ADDITIONAL PROCEDURAL TIMELINES FOR INTERCONNECTED MINI-GRIDS

1. A Distribution Licensee shall acknowledge receipt of a technical and investment proposal within five (5) business days.

2. A Distribution Licensee shall provide available Hosting Capacity Information and the minimum project-specific network data reasonably required for a System Impact Study within ten (10) business days of receipt of a complete request.

3. A Distribution Licensee shall notify the mini-grid developer within ten (10) business days whether a System Impact Study is sufficient or whether, for stated technical reasons, additional limited review is required.

4. A Distribution Licensee shall issue its technical response, including any conditions, reinforcement requirements, or reasons for refusal, within fifteen (15) business days after receipt of a completed System Impact Study or short-form submission.

5. Failure by the Distribution Licensee to respond within the applicable period shall amount to a deemed no-objection for the relevant procedural step only, and shall not amount to deemed energisation approval, deemed safety clearance, or deemed waiver of applicable technical requirements.

Fig. 1: Isolated or Interconnected mini-grid

I have located an Area

Is Main Grid Present?

Yes

No, it is an unserved area

Yes

Has it been assigned to an IEDNO or any other mini

-

grid Developer

?

No

I cannot go further

With the area

Is it part of an already existing expansion plan (5-year plan) of the Distribution Licensee?

Yes

No

I contacted the Distribution licensee to seek consent for operating in the area.

I could build and operate

isolated Mini

-

grid

Can I reach an agreement with the Distribution licensee licensee?

No

Yes

I cannot go ahead with the area

Is it an underserved Area

?

The grid does not provide a sufficient level of service according to the Community’s perception and community is prepared to pay higher tariffs to get access to reliable electricity supply

No

Yes

I can go ahead to operate an IMG.

I cannot go  ahead with the area

See the chart on isolated Mini

-

grid

See the chart on IMG

I am eligible to operate an IMG

I directly sign an agreement for an exclusivity period of not more than 12 months with the Distribution licensee & the community (Schedule 1-Agreement for exclusivity period for a mini-grid

I do not want to have an exclusivity period for the area

I receive the approval for tripartite

contract and a permit from NERC

I can install and commission the system

I first want an exclusivity period less than 12 month (I can    extend this period later)

I have established contact with the Distribution Licensee and the Community

I want to have an exclusivity period in the area

I have reached an agreement for a Tripartite agreement with the Distribution licensee and the community schedule 11 Tripartite agreement for interconnected mini grid.

I need an extension beyond 12 months. I sign an extension form with the Distribution licensee and the community (Form A – Supplementary Exclusivity Period Request Form)

I submit the executed tripartite agreement to NERC for approval (Schedule 11 Tripartite agreement for interconnected mini grid)

Fig. 2: Interconnected Mini Grid

Fig. 3: Isolated Mini Grid

I could build and operate an isolated Mini-grid

I submit my application form for a permit to NERC (Schedule 03 Application for permit)

I need an extension beyond 12 months. I submit application for extension to NERC (Schedule 1Agreement for exclusivity period)

I want an exclusivity period of 12 month (I can extend this period later) and sign exclusivity agreement with the community

I do not want to have an

exclusivity period for the area

My system has >100kw of distributed power and <=1MW installed generation capacity

I receive approval for the permit from NERC. I can install, commission and operate the isolated mini-grid

I establish contact with the Community and Distribution Licensee

I want to have an exclusivity period in the area

Is the distributed power of my mini-grid <=100kw?

I receive the approval for the exclusivity period from NERC

I do not need an extension beyond 12 months

I prepare all documents required for the permit (design, assets, authorizations, acquired, tariffs etc) according to Schedule 03 Application for permit

My system has <=100kW of distributed power

I register my mini-grid and submit the filled registration form to NERC (Schedule 2 Registration form for mini-grid under 100kW)

I start installing and commissioning the system

I prefer applying for a permit.

|  | Operation | - Used oil and oil filters shall be collected and disposed of in an environmentally friendly (safe) way. - Select site to meet the following requirements: - Noise Emission should be limited to an extent acceptable by the neighbors. | - Must only be operated on by trained technicians. - Must be in a safe working environment. - A comprehensive occupational safety program, including training and site orientation. - Testing and monitoring of air quality is strictly conducted where employees may be exposed to harmful substances, including worker respiratory protection and an emergency response plan. - Competent persons to effectively respond to emergency events. - Use safety barricade for work area to prevent unauthorize access. - Workers must wear Appropriate PPE. - Keep a record of all occupational injuries and illnesses and divulge these records to the Commission or the body on demand for examination and analysis. - Functional risk management process. - Should have a comprehensive insurance policy to adequately cover facilities, employees and third parties. - A permit-to-work system shall be strictly observed for all maintenance activities, and all original equipment manufacturer (OEM) recommendations for preventive maintenance and spare parts shall be complied with. |
| --- | --- | --- | --- |
|  | Decommissioning & Disposal | - Used oil and oil filters shall be collected and disposed of in an environmentally friendly way. - Compliance with Nigerian Electricity Health and Safety Standards Manual Provision in sections. | - Shall be conducted by competent persons. - Use certified lifting equipment for all lifting operations. |
| Solar PV | Operation |  | - Wear safety gear. - Shall be a safe working environment. - A comprehensive occupational safety program, including training and site orientation. - Competent persons to effectively respond to emergency events. - Keep a record of all occupational injuries and illnesses and divulge these records to the Commission or the body on demand for examination and analysis. - Functional risk management process. - Should have comprehensive insurance policy to adequately cover facilities, employees and third parties. |
|  | Decommissioning & Disposal | - For CdTe modules: Hazardous Waste must be collected and brought to a recycling centre. - Consult manufacturer’s guidelines or where necessary the manufacturer |  |
| Wind Turbine < 50 kW | Transport & Storage |  | - Use appropriate lifting and installation equipment due to the weight of the equipment (e.g., crane). |
|  | Installation | - Select site to meet the following requirements: - Noise Emission should be limited to an extent acceptable to the neighbours. Shading shall not be more than acceptable to the neighbours. - Must comply with Government laws and Regulations on applicable noise pollution. (Noise standards & control) | - Use appropriate lifting and installation equipment due to the weight of the equipment, (e.g., crane). - By selecting the site, take into consideration the ground characteristics for integrity of the turbine |
|  | Operation | - Switch off wind turbine during main flying hours of bats. - Used oil and oil filters shall be collected and disposed of in an environmentally friendly way. | - Maintain moving parts regularly according to the requirements of the manufacturers. - Must be a safe working environment. - A comprehensive occupational safety program, including training and site orientation. - Competent persons to effectively respond to emergency events. - Permit to work (PTW) system including Log Out Tag Out (LOTO) must be followed in all maintenance activities. - Ensure use of appropriate PPE - Keep a record of all occupational injuries and illnesses and divulge these records to the Commission or the body on demand for examination and analysis. - Functional risk management process. - Should have comprehensive insurance policy to adequately cover facilities, employees and third parties. |
|  | Decommissioning & Disposal |  | - Use appropriate lifting and installation equipment due to the weight of the equipment (e.g., crane). |
| Hydro < 50 kW | Transport & Storage |  | - Use appropriate lifting and installation equipment due to the weight of the equipment (e.g., crane). |
|  | Installation | - Comply with the water rights and related legislation. | - Moving parts of machinery must be designed and constructed in such a way as to prevent risks of contact which could lead to accidents or must, where risks persist, be fitted with guards or protective devices |
|  | Decommissioning & Disposal | - Comply with the water rights and related legislation. - Used oil and oil filters shall be collected and disposed of in an environmentally friendly way. | - See Transport & Storage |
| Biomass | Transport & Storage | - Sewage from biomass shall be kept from entering the ground water. - Biogas shall be stored in a way to minimize losses to the atmosphere (reduce greenhouse gas emission) | - Depending on the type of biomass, the biomass may carry the risk of fire. Therefore, it shall be stored in a safe fire-protected place. |
|  | Installation |  | - Use appropriate lifting and installation equipment due to the weight of the equipment (e.g., crane). |
|  | Operation | - Use appropriate Fire protection. - Must be a safe working environment. - A comprehensive occupational safety program, including training and site orientation. - Competent persons to effectively respond to emergency events. - Keep a record of all occupational injuries and illnesses and divulge these records to the Commission or the body on demand for examination and analysis. - Functional risk management process. - Should have a comprehensive insurance policy to adequately cover facilities, employees and third parties. - A safe system of work must be followed for all Operation and Maintenance activities. |  |
|  | Decommissioning & Disposal | - Any lubrication oil needs to be disposed off in an environmentally friendly manner. - The flow of river as it has been before installation of the equipment has to be reestablished | - Use appropriate lifting and installation equipment due to the weight of the equipment (e.g., crane). - Follow OEM’s recommendations for equipment de-commissioning. |
| Inverters, charge controller and other electronic equipment | Installation |  | - Shall only be installed by competent persons. |
|  | Operation |  | - Must be a safe working environment. - A comprehensive occupational safety program, including training and site orientation. - Competent persons to effectively respond to emergency events. - Keep a record of all occupational injuries and illnesses and divulge these records to the Commission or the body on demand for examination and analysis. - Functional risk management process. - Should have comprehensive insurance policy to adequately cover facilities, employees and third parties. |
|  | Decommissioning & Disposal | - Shall be disposed of in an environmentally friendly way. Waste must be collected and brought to a recycling centre. |  |
| Switch Gear and Distribution Box Conductors Transformers | Transport & Storage |  | - Use appropriate lifting and installation equipment due to the weight of the equipment (e.g., crane). |
|  | Installation | - Select a site where the risk of flooding is low. - Use fire proved material. - Make provision for oil containment where applicable. | - Installation only by an electrician - Wear all applicable safety gear like safety shoes and safety gloves. - Comply with the Distribution Code. |
|  | Operation | - Care must be taken to prevent oil leakage from transformers and other switchgears. | - Shall be a safe working environment. - Wear appropriate safety gear. - Shall only be operated by trained electricians. - Comply with the Distribution Code. - A comprehensive occupational safety program, including training and site orientation. - Competent persons to effectively respond to emergency events. - Keep a record of all occupational injuries and illnesses and divulge these records to the Commission or the body on demand for examination and analysis. - Functional risk management process. - Should have comprehensive insurance policy to adequately cover facilities, employees and third parties. |
|  | Decommissioning & Disposal | - Upon decommissioning, all foundations shall be removed and the site restored, as far as practicable, to its original condition. - Transformer may contain hazardous and polluting material which must be brought to a collection point where it can be treated. | - Use appropriate lifting and installation equipment due to the weight of the equipment (e.g., crane). - Appropriate protective equipment should be used by persons involved in the de-commissioning exercise. - Access to project/de-commissioning site must be restricted to only persons involved in the decommissioning exercise. |

I, _______________ (name), representative of Mini-Grid Developer/Operator name: ________________________ Mini-Grid Developer/Operator address: ________________________________________________________________Company registration number: _____________________________ am applying for a Permit and therefore warrant that I will comply with the above-mentioned environmental, health and safety guidelines.

In the event of any failure to comply with these guidelines, I am conscious that the competent authorities can impose fines according to the gravity of the infraction.

Date:

Company Representative